## Slide 1: Moving ChadaTech to Scrum
Lessons from the SNHU Travel pilot
Brendan Malloy, Scrum Master
Prepared for ChadaTech leadership, October 2026
Notes: I served as the Scrum Master for the SNHU Travel pilot, and over the course of the project I also worked as the Product Owner, a Developer, and the Tester. ChadaTech has used the waterfall model for years, and leadership asked our team to try Scrum first. This presentation explains the Scrum roles, how the phases of the software development life cycle work in an Agile approach, how our project would have gone under waterfall, and the factors I would weigh when choosing between the two.

## Slide 2: The SNHU Travel pilot at a glance
THE PILOT
6
user stories in the Product Backlog
3
detailed stories with acceptance criteria
6
test cases, three written and three revised
2
changes in direction during the project
5
weeks on the client's timeline
The client
SNHU Travel wants to grow with niche vacation packages and asked for a working booking site in five weeks.
How I worked
One role at a time: Product Owner, Developer, Tester, and now Scrum Master for this review.
Notes: SNHU Travel is a travel agency that wants to reach more customers with niche vacation packages. Amanda, the client, wanted a working booking site within five weeks. These numbers come straight from the work our team produced. As Product Owner I turned a focus group meeting into six ranked user stories and wrote three of them out in detail with acceptance criteria. As Tester I wrote three test cases and then revised all three when the Product Owner sent a new wireframe. The project changed direction twice, once to a one-destination-per-slide format and once to detox and wellness travel. Because I worked each role, I can speak to what each one needed from the others.

## Slide 3: Four roles, one owner for each decision
AGILE ROLES
Product Owner
Owns the Product Backlog and decides what the team builds next.
Pilot: ranked six focus group stories
Scrum Master
Runs the Scrum events, coaches the team, and clears impediments.
Pilot: routed new work through Christy
Developer
Builds a usable increment every Sprint and owns the Sprint Backlog.
Pilot: built the list and slide show
Tester
Turns acceptance criteria into pass and fail checks.
Pilot: revised tests for the wireframe
In Scrum, developers and testers together form the Developers. Stakeholders such as Amanda sit outside the team and shape the backlog at the Sprint Review (Coleman, 2024; Jocham et al., 2025). Clear roles keep the team close to those needs (Verwijs & Russo, 2023).
Notes: Scrum gives every kind of decision a single owner, and that is the main reason the roles matter. The Product Owner owns the Product Backlog and its order. On our team that was Christy. One person deciding what comes next kept us from building features out of order, and it gave the Developers one place to take questions. The Scrum Master runs the Scrum events, coaches the team on the process, and removes impediments. The Scrum Master does not assign work. On our team, Ron made sure nobody went around Christy to hand unplanned work straight to a Developer. The Developers build a usable increment every Sprint. Coleman (2024) explains that they own the Sprint Backlog and adjust it as they learn, as long as the work still moves toward the Sprint Goal. When I built the Top Five Destinations list, I added a landing page because the first acceptance criterion said the user clicks a link to reach the list. The Tester is part of the Developers in Scrum terms, but on our team it was a separate job: turning each acceptance criterion into a pass and fail check before a story counts as done. Stakeholders such as Amanda are not on the Scrum Team. The Scrum Guide Expansion Pack places them in the environment around the team (Jocham et al., 2025), and they shape the work through the Sprint Review. Verwijs and Russo (2023) found that Scrum teams are more effective when they stay close to stakeholder needs and can respond to them quickly. Clear roles are what make both of those possible.

## Slide 4: Agile repeats every SDLC phase each Sprint
AGILE PHASES
One Sprint
repeated until done
1
1
Plan and analyze: pick the highest-value stories and agree on a Sprint Goal.
2
2
Design: sketch only what this Sprint needs, such as one wireframe.
3
3
Code: build a small piece of working software.
4
4
Test: check each acceptance criterion inside the Sprint, not after it.
5
5
Deploy: deliver a usable increment the client can try.
6
6
Review and maintain: feedback and the Retrospective shape the next Sprint.
Phase names follow Jackson et al. (2025).
Notes: Agile does not remove the phases of the software development life cycle. Jackson et al. (2025) list planning, analysis, design, coding, testing, deployment, and maintenance, and they point out that waterfall completes those phases in sequence while an iterative approach like Agile works on them in parallel and in short cycles. In Scrum, every Sprint is a small pass through all of them. Planning and analysis matter because they point the team at the most valuable work first. In Sprint Planning the team agrees on a Sprint Goal and pulls the top stories from the backlog. Design matters because a quick sketch costs far less than code that gets thrown away. Our Product Owner's wireframe was enough design for that Sprint. Coding produces something real the team can inspect, not a document about it. Testing inside the Sprint means defects are found while the code is fresh, and a story is not done until its acceptance criteria pass. Deployment puts a usable increment in front of the client, which is where the real feedback comes from. Review and maintenance close the loop. The Sprint Review collects stakeholder feedback, the Retrospective improves how the team works, and both feed the next Sprint Planning.

## Slide 5: How the phases ran on SNHU Travel
AGILE PHASES
Phase | What we did on SNHU Travel | Where it happens in Scrum
Plan and analyze | Turned the focus group into six ranked, sized user stories | Backlog refinement, Sprint Planning
Design | Christy shared a wireframe with one destination per slide | Sprint Planning
Code | Built the Top Five list, then the wellness slide show | The Sprint, Daily Scrum
Test | Wrote three test cases, then revised all three for the wireframe | The Sprint, Daily Scrum
Deploy | Exported a runnable JAR so the Tester ran the same build | End of the Sprint
Review and maintain | Demo the increment to Amanda; agree on one improvement | Sprint Review, Sprint Retrospective
Every phase showed up in every Sprint, just at a smaller size.
Notes: Here is what each phase looked like on our project. Planning and analysis started with the Product Owner focus group. I turned what the users said into six user stories, sized each one, and ranked them, so the Top Five Destinations list came first. Design was light. When I asked the Product Owner questions about my test cases, she answered with a wireframe that showed one destination per slide with Previous and Next buttons. Coding produced the Top Five Destinations list in Java Swing and, later, the wellness slide show. Testing happened in the same Sprint as the code. Each acceptance criterion became a step with a pass and fail measure, and when the wireframe changed the screen, I revised all three test cases. Deployment was an exported JAR file, which meant the Tester ran exactly the build the Developer delivered. Review and maintenance happen at the Sprint Review, where the increment is shown to Amanda, and at the Retrospective, where our charter says the team agrees on one improvement. The point is that no phase was skipped. Each one just happened at a smaller size, many times.

## Slide 6: Waterfall runs each phase once, in order
WATERFALL MODEL
Requirements
Design
Implementation
Testing
Deployment
Maintenance
Each phase is signed off before the next one starts.
Work moves in one direction.
Each phase is finished before the next begins, so a late change goes back up the chain.
(Jackson et al., 2025)
The client sees results late.
Customers mostly take part during planning at the start and evaluation at the end.
(Mishra & Alzoubi, 2023)
Best for stable requirements.
It fits when the requirements are well defined and unlikely to change.
(Mishra & Alzoubi, 2023)
Notes: In the waterfall model, the same phases run once, in a fixed order. Requirements are gathered and approved, then the whole system is designed, then built, then tested, then deployed and maintained. Jackson et al. (2025) describe waterfall as completing the phases sequentially, which is the key difference from Agile. Mishra and Alzoubi (2023) compared structured and agile development and found that customers in a structured model take part mainly during initial planning and final evaluation, while agile depends on customers being engaged throughout. They also found that waterfall works best when requirements are well defined and stable from the start, and that agile suits projects where requirements are unknown or likely to change. Waterfall is not a bad model. It gives clear documentation and predictable milestones. The problem is that it assumes we know what the client wants before we start, and on SNHU Travel we did not.

## Slide 7: The wellness change under each approach
WATERFALL VS. AGILE
Midway through the project, SNHU Travel moved the booking tool to detox and wellness travel.
Under Scrum: what happened
Christy kept the finished work and changed only the vacation types.
I kept the slide show navigation and swapped in five wellness trips.
My questions went to Christy and the Tester before the Daily Scrum.
Test cases were updated in the same Sprint as the code.
Under waterfall: what it would take
Requirements were already signed off, so a formal change request starts.
Design documents are reopened and approved again.
Code written to the old plan gets reworked after approval.
Testing waits until the end, when defects cost the most to fix.
Cost under Scrum: one updated slide show and a revised set of test cases.
Notes: This is the clearest example of the difference from our project. Midway through, SNHU Travel management decided the booking tool should focus on detox and wellness travel. Under Scrum, Christy made it clear that existing work was not being thrown out and that only the vacation types had to change. As the Developer, I kept the slide show navigation that already worked and replaced the five slides with wellness trips. I sent my questions to Christy and the Tester and asked for answers before the next Daily Scrum, so nothing sat waiting. The test cases were updated in the same Sprint. Under waterfall, the requirements would already have been signed off. The change would need a formal change request, the design documents would be reopened and approved again, any code written to the old plan would be reworked, and testing would not start until the build was finished. The earlier wireframe change shows the same thing on a smaller scale. Because I was writing test cases during the Sprint, my questions to the Product Owner surfaced the slide show format before any code depended on it. In waterfall, test cases are usually written after the build, so a mismatch like that might not show up until system testing.

## Slide 8: Choosing waterfall or Agile
CHOOSING AN APPROACH
Factor | Agile fits when | Waterfall fits when | SNHU Travel pilot
Requirement stability | Needs will change as users see the product | Requirements are known and stable at the start | Changed twice in five weeks
Client involvement | The client can review work every Sprint | The client is mainly available at the start and end | Amanda reviews each increment
Size and team spread | A small team that works closely together | A large project with teams spread across sites | One small Scrum Team
Cost of late change | Late changes must stay cheap | Change is rare and formally controlled | The wellness change came mid-project
Delivery timeline | The client needs working software early | One full release on a fixed date is acceptable | Five-week deadline
Factors 1 to 3 draw on Mishra and Alzoubi (2023). Factors 4 and 5 come from the pilot. Every row pointed SNHU Travel toward Agile.
Notes: These are the factors I would weigh when choosing an approach for a new ChadaTech project. The first three come from Mishra and Alzoubi (2023). Waterfall fits best when requirements are well defined and stable, while agile suits requirements that are unknown or likely to change. Agile also depends on a customer who stays engaged through development, while waterfall involves the customer mostly at the start and the end. On size, they found agile favored for small projects and waterfall more suitable for large ones, and they suggest a hybrid for large projects with dispersed teams. The last two come from our pilot. When change arrives mid-project, Agile keeps the cost low because the work is already split into small pieces. When the client needs working software quickly, as Amanda did with a five-week deadline, Agile delivers usable increments along the way. For SNHU Travel, every row pointed toward Agile. The requirements came from a focus group and changed twice, the client could review work each Sprint, and we were one small team. A project with a fixed scope, a large distributed team, or heavy sign-off requirements could reasonably land on the waterfall side or on a hybrid.

## Slide 9: Adopt Scrum and keep a plan-driven option
RECOMMENDATION
01
Use Scrum for evolving work
Client projects whose needs will shift, like SNHU Travel, which absorbed two changes without a restart.
02
Keep waterfall for fixed scope
Stable, well-defined work with formal sign-offs still fits a plan-driven or hybrid model (Mishra & Alzoubi, 2023).
03
Carry the pilot's lessons
Write acceptance criteria with measurable limits, keep decisions on a shared board, and protect the Product Owner's time.
Notes: My recommendation is that ChadaTech move its client teams to Scrum, while keeping a plan-driven option for the right kind of project. First, use Scrum for work whose requirements will evolve. SNHU Travel changed direction twice, and both changes were handled inside a Sprint without starting over. Second, keep waterfall or a hybrid available for projects with fixed scope and formal sign-offs. Mishra and Alzoubi (2023) found that structured development fits stable, well-defined requirements and that hybrids can serve large projects with dispersed teams. Third, carry three lessons from the pilot. Our acceptance criteria had no measurable limits, such as page load time, so testers had to guess at pass measures. Our decisions lived in email, where they were easy to lose, so a shared board such as Azure Boards or Jira should hold them on the work item. And work that needed the Product Owner's answer sat still until she replied, so teams need protected Product Owner time.

## Slide 10: References
SOURCES
Coleman, J. (2024, October 17). Developers accountability in Scrum. Scrum.org. https://www.scrum.org/resources/blog/developers-accountability-scrum
Jackson, G., Holdsworth, J., & Kosinski, M. (2025, January 2). What is the software development life cycle (SDLC)? IBM. https://www.ibm.com/think/topics/sdlc
Jocham, R., Coleman, J., & Sutherland, J. (2025). Scrum guide expansion pack. https://scrumexpansion.org/scrum-guide-expansion-pack/
Mishra, A., & Alzoubi, Y. I. (2023). Structured software development versus agile software development: A comparative analysis. International Journal of System Assurance Engineering and Management, 14(4), 1504-1522. https://doi.org/10.1007/s13198-023-01958-5
Verwijs, C., & Russo, D. (2023). A theory of Scrum team effectiveness. ACM Transactions on Software Engineering and Methodology, 32(3), Article 74. https://doi.org/10.1145/3571849
Notes: These are the five sources cited in this presentation, formatted in APA style. All were published within the last five years.